## Proposed Plan
MONTHS
# | Activity | Participants | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
1 | Define EIQC ISO Project Scope/Project Team/ Establish POA&M
2 | Conduct ISO 9001 Project Management Overview
3 | Conduct ISO 9001 Requirements Training with EIQC Employees
4 | Define Documentation Platforms/Control Structure
5 | Perform a Gap Assessment of the EIQC Existing Systems
6 | Individual owners review/redline EIQC procedures
7 | Define EIQC Organizational Structure (Titles & Job Descriptions)
8 | Formalize 4.2.3 - Document Control
9 | Review/incorporate initial redline inputs received
10 | Draft 7.3 - Design Control procedures
11 | Conduct team review of the procedures
12 | Incoporate changes from team review
13 | Distribute revised procedures for author approval
14 | Review all final draft procedures
15 | Rev.1 procedures approved, published & distributed
16 | Quality manual draft prepared
17 | Define, develop and write draft work instructions
18 | Quality manual draft reviewed
19 | Rev. 1 quality manual approved and released
20 | Submit application & quality manual to registrar
21 | Work instruction drafts reviewed
22 | Rev. 1 work instructions approved and released
23 | Employee training on policies/procedures/WI's
24 | Implement procedures/self audit
25 | Conduct Internal Audit Training
26 | First Internal audits completed
27 | Corrective actions developed and implemented
28 | Effectiveness of corrective actions verified
29 | Management review meetings
30 | Pre-assessment is conducted by the Registrar
31 | Corrective actions from pre assessment
32 | 2nd internal audits completed
33 | Corrective actions developed and implemented
34 | Effectiveness of corrective actions verified
35 | ISO 9001 Awareness/Audit Preparation Training
36 | Formal assessment is conducted by the Registrar
37 | EIQC Corrective Action is submitted to the Registrar